## Sheet1
Issue Number | UserStory | Story Points | Reasons
27 | As a seller, I want to be able to find my customer's email address, because I want to be able to contact them to discuss something about their order. #27 | 1 | Finding a customer email address is an easy feature since the seller can just go into customer's profile.
41 | As a customer, I want to be directed to the product page when I click on the ad. #41 | 1 | Going to the product page of the ad is an easy feature since we just need to make the ad clickable leading to the website which can be done in the html quickly.
44 | As an admin, I want to be able to track the ads banned by the customers. #44 | 2 | Tracking ads appeared to the customer feature can just be done by adding all the ads apperaed to this customer to a data structure linked to his/her account in the database.
29 | As an admin, I want to be able to remove users, because the user requested to close/delete their account. #29 | 3 | this feature will just need to remove user's account from the database but it needs to be done carefully to not affect any other data in the data base.
28 | As an admin, I want to be able to change my password every now and then, because I want to make sure that the website security will not be compromised. #28 | 4 | this feature can be implemented by resusing some code used when we implemented the password for registring an account for the first time, so it won't take that much.
31 | As a Customer, I want to determine the quantity of the product that I will purchase, because I want all of them to be shipped in one order. #31 | 5 | This feature will need apparently 2 buttons and one variable for the quantity, but has more things to be taken into consideration while dealing with the database for this product.
43 | As a customer, I want to be able to ban a displayed ad. #43 | 6 | This will require an X button on the top right corner of the add to close it
42 | As a Seller, I want the customer to be able to add coupons on some of my products, because I want to encourage them to buy specific products. #42 | 7 | this feature will need 2 a list of all the valid coupons to compare the entered coupon to check its validity after this, we need to apply the discount on the total price
30 | As a seller, I want to be able to change the address from which I ship out my customers' packages, because I moved to a new warehouse.#30 | 8 | this feature will need in addtion to just update some data for the seller address, it will also need to check of the validity of the new address and it will affect the new pricess for the shipping on each product.
32 | As a Customer, I want to remove individual products from my cart directly, because I don't want to cancel the whole order just to remove one item from my cart. #32 | 8 | This feature will need an X button beside each product in the cart of the customer, moreover it needs Undo button to return the items removed by mistake from the cart.
45 | As an admin, I want to access the Wishlist of each user, because I want to show related products to each customer's interests.#45 | 9 | This feature will need some work cause firstly, we need to access the wisklist of each customer, Then put them into categories and then show the customer the products that tailored to his/her interests.
38 | As a seller, I want the cost of the product before and after the shipping fees to be showed, because I want to show the customer exactly the details of the purchase. #38 | 12 | this feature will take time cause we need to calculate the distance between the address of the seller of each product and the customer and then adds the shipping fees.
40 | As a seller, I want to be able to edit past posted ads. #40 | 15 | Editing ads will need more effort since first we should develop an algorithm for which past ads to be changed and which new ones should be replaced. Based on the responding of the customers with the ads
46 | As an admin, I want to block ads reported as inappropriate when banned by customers. #46 | 17 | this feature will take much time as well since we have to develop an algoritm to categorize ads and based on categorization, we should choose which ads to be banned and which should stay
39 | As a seller, I want to be able to post ads about products available on the e-commerce. #39 | 20 | being able to posting ads, this is one of the hardest features, since we choose proper places on the website to show these ads, then we should develop an algorithm to show ads to the right customers based on their interests and then link these ads to their products or websites.
47 | As an admin, I want an automatic email to be sent to the customer and the seller after each purchase, because I want this email as a confirmation of the purchase success. #47 | 20 | this feature is considered as one of the hardest features, since we will need to have a standard email to be sent but also it should have some variables that is customized based on the product purchased, customer info, seller info and payment info